## Slide 1
CAP2 process improvement
Action plan for faster changeovers and stable production
Focus areas
Rewind and crane cycle Setup reduction Hourly target screen Material and support calls
90 day implementation plan
Notes: Source: CAP2 Complete Process Improvement Plan, prepared from the supplied CAP2 time study, run-rate records, project plans and SOP Rev 12.

## Slide 2
Current state and main losses
The supplied records show high variation and large avoidable delays
Chart: 
| Material feeding | Roll change GRP | Roll change NPF/FF/RST | Mechanical issues | Waiting for material | Quality issues
Recorded minutes | 1145 | 527 | 467 | 414 | 390 | 238
67.6%
of coded downtime minutes came from the top five loss categories
21.4%
reported productive share. Validate the time records before treating this as formal OEE.
RST10 remains a product case study only. Every product family needs its own run-rate target.
CAP2 action plan 2
Notes: Source: Time study CAP 2 Rewind. Coded event sample totals 4,354 minutes across 185 events. The YTD summary reports 169.05 production hours and 621.05 downtime hours. RST10 figures are product-specific and do not represent all CAP2 products.

## Slide 3
Six action priorities
Each priority has a measurable operating result
01
Rewind restart
Start the next roll sooner. Separate restart work from wrapping where the approved method allows it.
Median repeat exchange at or below 2 min 30 sec
02
Crane and lifting
Reduce crane travel and attachment time. Develop a rated hook-bar lifting aid.
25% lower crane time and 30% faster attachment
03
Setup reduction
Use SMED to stage rolls, cores, tools, recipes and pallets before shutdown.
30% lower median setup time by Day 60
04
Point of use 5S
Move approved cores, wrap, tools and lifting gear closer to the operator.
No searching or missing-item delays
05
Material and scrap
Maintain two-job readiness and correct alignment, tension and flow problems at source.
50% fewer flow stops and 30% lower scrap by Day 90
06
Minor stops
Record interruptions over 30 seconds and close the top recurring petty issues.
80% reduction in the top 10 micro-stops
CAP2 action plan 3
Notes: Source: CAP2 Complete Process Improvement Plan, Sections 6.2 through 6.6. Targets are improvement goals subject to safety, quality and baseline validation gates.

## Slide 4
Rewind and crane improvement
Reduce the delay between a completed roll and the start of the next roll
1
Prepare
Stage the correct core, wrap, lifting bar and empty skid before the cut.
2
Unload
Position the crane at its home point and remove the completed roll safely.
3
Restart
Assign one panel owner to reset and start immediately after the safe all-clear.
4
Finish
Wrap, post and transfer the previous roll while production continues when the approved method allows it.
Engineering trials
Rewind speed
Increase by controlled SKU trials. Check tracking, dancer stability, roll tightness and stopping.
Crane speed
Confirm rated limits, load stability, stopping distance and control condition before adjustment.
Hook-bar lifting aid
Complete calculations, risk assessment, proof-load test, inspection standard and operator trial.
CAP2 action plan 4
Notes: Safety gate: no change may bypass guarding, light curtains, crane rules, two-person lift requirements or control interlocks. Crane speed and hook-bar changes require Engineering and EHS approval.

## Slide 5
Setup material and flow controls
Preparation moves outside machine downtime wherever possible
Before the stop
Confirm the next work order
Stage rolls, cores, rods and tools
Load recipe and work instruction
Confirm pallet, crane and forklift
During the stop
Remove depleted material
Install the prepared roll
Align and thread the layers
Complete the first-off check
After restart
Return empty cores
Record output and scrap
Replenish the next-job kit
Restore 5S without stopping production
Daily controls
Two-job readiness at least 95% by Day 60
Track scrap by product and defect reason
Escalate a repeated material-flow issue after the second occurrence
Review the top three micro-stops at each daily tier meeting
CAP2 action plan 5
Notes: Source: CAP2 Complete Process Improvement Plan, setup time reduction, material readiness, scrap control and minor-stop workstreams.

## Slide 6
Hourly production control and support calls
Operators see the active product target and receive support when the line falls behind
CAP2 HOURLY STATUS
Active product
VersaDUEL example
Hourly target
Product-specific target card
Actual this hour
Live count from posting, scanner or PLC
Gap and pace
Green on plan Amber recovery needed Red supervisor support
Supervisor escalation
Proposed logic: green at 100% or above, amber at 90% to 99%, and red below 90% or after two consecutive missed hours. The alert sends product, target, actual, gap, loss reason and requested support.
Support request buttons
MATERIAL NEEDED
SCRAP BIN PICKUP
MAINTENANCE
QUALITY SUPPORT
CORE PACKAGING OR FORKLIFT
Each request records call time, acknowledgement, arrival, completion and lost minutes. The screen shows request status, and overdue calls escalate to the shift supervisor.
CAP2 action plan 6
Notes: Proposed production-control logic. Hourly targets must come from the approved product-specific target card. Separate operator-controlled losses from material, maintenance, quality, forklift and scrap-service delays. Management must approve alert thresholds and response times.

## Slide 7
90 day execution plan
Changes advance only after safety quality and repeatability checks
Days 1 to 14
Measure
Reconcile production time
Complete 10-shift baseline
Observe setups and micro-stops
Accepted baseline and top loss list
Days 15 to 30
Pilot
Trial standard work
Launch hourly target screen
Test support buttons and response
Approved method and trained pilot crew
Days 31 to 60
Stabilize
Release product target cards
Complete speed and SMED trials
Fix top equipment losses
Downtime down 30% and audit at least 85%
Days 61 to 90
Control
Verify sustained results
Close hook-bar design gates
Transfer ownership to operations
Downtime down 50% and audit at least 90%
Immediate decisions
Approve the two-week baseline sprint
Assign owners for crane, rewind, setup, material and scrap actions
Approve alert thresholds, support response times and controlled trials
CAP2 action plan 7
Notes: Source: CAP2 Complete Process Improvement Plan, 90-day roadmap and governance sections. Add the hourly target screen and support-call system during the pilot phase, then validate alert logic and response times before full release.