# CAP2 Complete Process Improvement Plan

Current state baseline desired state and 90 day execution roadmap

Machine: CAP2 laminating and rewind line
Prepared for: Operations Engineering and CAP2 Production
Prepared: 23 September 2026
Baseline window: supplied YTD summary and detailed records through 21 September 2026

Decision required

Approve a controlled 90 day improvement program focused first on data integrity, continuous flow at rewind, material readiness and standardized operator work. Use product-specific targets rather than a single 80-roll target for every item.

Main conclusion

CAP2 produces multiple products with different lengths, constructions, setup requirements and achievable rates; therefore, the machine must not be managed to one universal roll target. RST10 is used only as a product-specific case study because it has the strongest comparable run history in the supplied data. For RST10, demonstrated rewind capability supports 80 rolls in a 10-hour productive window, while recorded execution averages about 60.6. Across the line, the primary opportunity is to stabilize material feeding, roll changes, material availability, restart discipline and crane-supported handling while protecting safety and quality.

# Executive summary

This plan converts the supplied CAP2 time study, run-rate calculator, project notes and Rev 12 SOP into a measurable improvement system. It establishes a defensible baseline, identifies the main operating losses, defines the future condition and assigns a phased route to reach it.

| Finding | Current evidence | Meaning |
| --- | --- | --- |
| Overall utilization signal | 1,188 rolls; 169.05 production hours; 621.05 downtime hours in the supplied YTD summary | Reported productive share is 21.4%. This is a strong loss signal but must be reconciled before it is treated as formal OEE availability. |
| RST10 product case study | 737 rolls over 121.58 elapsed hours across 15 listed runs = 9.90 min/roll or 6.06 rolls/hour | Equivalent to about 60.6 rolls per 10 production hours for this product only. It is not the CAP2 line-wide rate. |
| RST10 direct time study | Nine 15 ft observations average 5.62 min/roll = 10.68 rolls/hour | The work cycle can support the 8 rolls/hour standard when losses are controlled. |
| 25 ft direct study | Two observations average 12.56 min/roll = 4.78 rolls/hour | An 80-roll target is not realistic for this studied 25 ft condition; initial planning target should be product-specific. |
| Loss concentration | 185 coded events total 4,354 min; top five categories account for 67.6% | Material feeding, major roll changes, mechanical issues and waiting for material should lead the action plan. |

## Recommended performance commitments

Use RST10 as the first product-specific pilot: stabilize it at 8.0 good rolls/hour and 80 good rolls per 10 productive hours by Day 60, then apply the same target-setting method to other product families.

Set separate standards for every product family using the existing run-rate model and verified observations. Do not apply 80 rolls to 15 ft, 25 ft and 54 ft products indiscriminately.

Reduce controllable downtime minutes per scheduled hour by 30% from the verified two-week baseline by Day 60 and 50% by Day 90.

Reduce median material-feeding event duration from 24.9 minutes average to 15 minutes by Day 60 and 10 minutes by Day 90.

Complete routine outfeed roll removal, core loading and restart within 2 min 30 sec when the SOP allows parallel work; verify with at least 30 cycles.

Increase approved crane and rewind speeds through controlled trials, then develop an engineered hook-bar lifting aid to reduce attachment and transfer time without introducing lifting or dropped-load risk.

Move cores and repeat-use tools to point-of-use locations, reduce setup through SMED, maintain two-job material readiness, and eliminate recurring minor stops that repeatedly interrupt flow.

Display the active product hourly target and live actual output on an operator screen. Alert the shift supervisor when performance falls below the approved threshold and provide support-call buttons for material, scrap-bin pickup, maintenance, quality, cores, packaging and forklift assistance.

Maintain zero recordable safety incidents and no deterioration in first-pass quality while changing work methods or speed.

## Management gates

| Gate | Timing | Release criterion |
| --- | --- | --- |
| Baseline accepted | End Week 2 | At least 10 representative shifts; clean planned/unplanned time; good quantity, scrap and downtime reconciled to shift duration. |
| Standard work released | End Week 4 | Safe method approved; operators trained; 30 observed cycles; no unresolved quality or guarding concern. |
| Performance proven | End Week 8 | RST10 pilot at or above 8.0 good rolls/hour on five comparable runs; separate target cards issued for other priority product families; top loss minutes down at least 30%. |
| Control transferred | End Week 12 | Four-week control charts stable; layered audits above 90%; owners and reaction plan active. |

# 1 Scope method and evidence

## 1.1 Scope

The improvement boundary begins with scheduled material and consumables available at CAP2, includes unwind loading, threading, lamination, cutting, rewind, wrapping, crane transfer and posting, and ends when a conforming roll is placed on the WIP skid. Upstream material shortages and downstream forklift response are included where they stop this boundary process.

## 1.2 Evidence reviewed

| Source | Use in this plan |
| --- | --- |
| Time study CAP 2 Rewind | Direct cycle observations; YTD production and downtime summary; run history; detailed downtime-event sample. |
| CAP2 Run rates spreadsheet PDF | Product setup assumptions, line-speed assumptions, finished lengths and calculated run rates. |
| CAP 2 Project Plan and CAP 2 Plan | Existing improvement intent, observed stoppages, proposed role changes and 2 min 30 sec cycle-restart expectation. |
| Pliteq 084-SOP-001 CAP2 Rev 12 | Current three-operator responsibilities, safety controls, operating sequence, rewind unloading and material-change methods. |

## 1.3 Data limitations that must be corrected

The YTD summary reports 621.05 downtime hours, while the extractable coded-event sample totals 4,354 minutes or 72.6 hours. These appear to be different scopes or incomplete exports and must not be combined without reconciliation.

The shift summary shows 371 downtime hours for CD2 but only 0.56 hour for CN1, an imbalance requiring validation of logging behavior and time boundaries.

Some production records show implausible results such as 8 rolls in 1 minute or large quantities below one minute per roll. These records should be quarantined until the start and stop logic is confirmed.

The 25 ft time study contains only two observations; the 15 ft study has nine. Neither is enough to lock a permanent engineered standard across all operators and products.

Quality yield and scrap quantities are absent from the performance summary, so formal OEE cannot yet be calculated. This plan uses good-roll rate and loss minutes until quality data are available.

Baseline rule: Weeks 1 and 2 will create the official baseline. Values in this report are an initial analytical baseline and are deliberately labeled as recorded, observed or calculated.

# 2 Current process and operating state

## 2.1 High level process

| Stage | Primary work | Current exposure |
| --- | --- | --- |
| Prepare | Review work order; stage rolls, cores, wrap, pallets and tools | Waiting for material; late forklift response; pre-shift and 5S time occurring inside scheduled production. |
| Load and feed | Crane-load unwind rolls; align and thread material | Material feeding is the largest coded loss; all operators may be pulled into feed activity. |
| Laminate | Run belts, heater, calibration and cooling at recipe settings | Heater/mechanical faults; misalignment; belt contamination from glue or brown-sheet problems. |
| Cut and rewind | Cross-cut to length; secure material on core; rewind | Foot-pedal response delay; dancer-bar lower-limit stops; roll-cut stops; rewind speed opportunity. |
| Unload and restart | Release chucks; crane-transfer roll; insert core; reset and restart | Crane cannot always keep pace; sequential work creates belt waiting and restart delay. |
| Wrap and stage | Stretch-wrap completed roll; transfer to WIP skid; post production | Wrapping and crane work compete with restart; late posting obscures actual output. |

## 2.2 Existing staffing concept

Rev 12 assigns one West operator to infeed, one East Group 1 operator to HMI/outfeed and crane unloading, and one East Group 2 operator as a floating helper who also rewinds, wraps and performs inspections. The intended design supports parallel work, but several procedures still require operators to converge on feeding, lifting or crane tasks. The improvement must therefore clarify what can be parallelized and what must remain synchronized for safety.

## 2.3 Observed rewind cycle

| Element | 15 ft study average | 25 ft study average | Improvement implication |
| --- | --- | --- | --- |
| Initial roll setup | 0.67 min | 1.91 min | Pre-position core and materials; define ready-to-start condition. |
| Rewinding | 1.93 min | 5.80 min | Confirm safe maximum recipe speed and foot-pedal response. |
| Wrapping | 1.23 min | 2.27 min | Begin new cycle before completing wrap where SOP permits. |
| Pre-crane pickup | 0.35 min | 1.25 min | Standardize strap and crane-ready position. |
| Crane drop-off | 0.72 min | 1.12 min | Optimize layout and crane travel path. |
| Restart buffer | 0.42 min observed subset | 0.23 min | Use one restart owner and visible ready signal. |
| Total | 5.62 min/roll | 12.56 min/roll | Targets must vary by product length and construction. |

# 3 Baseline performance

## 3.1 Initial KPI baseline

| KPI | Initial baseline | Calculation or source | Interpretation |
| --- | --- | --- | --- |
| Reported productive share | 21.4% | 169.05 production h / (169.05 + 621.05 downtime h) | Data-defined utilization signal, not approved OEE availability. |
| Overall recorded production rate | 7.03 rolls/production h | 1,188 / 169.05 h | Mix-dependent; cannot be used as a universal product standard. |
| RST10 weighted elapsed rate | 6.06 rolls/h | 737 rolls / 121.58 h across 15 listed records | Product-specific case-study indicator; not the CAP2 line-wide standard. |
| RST10 weighted cycle | 9.90 min/roll | 7,295 elapsed min / 737 rolls | 32% slower than the stated 7.5 min standard. |
| RST10 row median cycle | 9.85 min/roll | Median of 15 run-level rates | Confirms the weighted average is representative. |
| RST10 direct-study cycle | 5.62 min/roll | Nine observed cycles | Demonstrated local capability; not sustained shift performance. |
| 25 ft direct-study cycle | 12.56 min/roll | Two observed cycles | Provisional only; collect at least 30 cycles. |
| Coded downtime sample | 4,354 min; 185 events | Detailed supplied event records | Use for priority ranking, not reconciliation to YTD total. |

RST10 case-study interpretation: At 9.90 min/roll, this product produces about 60.6 rolls in 10 elapsed production hours. At its current stated standard of 7.5 min/roll, output is 80. The direct-study mean of 5.62 min/roll indicates a local technical capability of about 106.8 before normal allowances. None of these values should be applied to another CAP2 product without its own study.

## 3.2 Downtime Pareto

| Priority | Loss category | Minutes | Events | Share | Initial response |
| --- | --- | --- | --- | --- | --- |
| 1 | Material feeding | 1,145 | 46 | 26.3% | Standard threading method; prepare next roll; rapid-response escalation. |
| 2 | Roll change GRP | 527 | 14 | 12.1% | Internal/external SMED split; pre-stage crane, rod and roll. |
| 3 | Roll change NPF FF RST | 467 | 18 | 10.7% | Pre-stage and define handoffs; trial safe parallel tasks. |
| 4 | Mechanical issues | 414 | 18 | 9.5% | Defect tagging; top failure Pareto; planned corrective work. |
| 5 | Waiting for material | 390 | 11 | 9.0% | Two-job material readiness board and supplier signal. |
| 6 | Breaks | 335 | 13 | 7.7% | Separate planned break from downtime and confirm relief approach. |
| 7 | Quality issues | 238 | 11 | 5.5% | First-off checklist and defect reaction standard. |

Focus rule: The top five categories represent 67.6% of coded minutes. Improvement resources should not be diluted across every loss at once.

# 4 Root cause assessment

## 4.1 Loss tree and working hypotheses

| Problem | Likely mechanisms supported by the files | Confirmation method |
| --- | --- | --- |
| Low and unstable output | Mixed product standards; stops embedded in elapsed time; slow restart; inconsistent crew execution | Stratify by SKU, crew and shift; video-safe elemental study; hourly board. |
| Material feeding loss | New material not prepared; alignment complexity; all operators required; repeated threading; missing layers | Observe 10 events by product; spaghetti map; separate waiting, motion and hands-on time. |
| Long roll changes | Crane travel; roll/rod not staged; serial unload/load; unclear readiness ownership | SMED worksheet on 10 GRP and 10 NPF/FF/RST changes. |
| Rewind interruption | Foot-pedal delay; dancer reaches lower limit; belts restart late; crane lags finished rolls | PLC/HMI event timestamps; verify pedal-to-drive and dancer-to-belt logic with Controls. |
| Waiting for material | No confirmed next-job kit; supply request too late; forklift response not measured | Two-job look-ahead board; timestamp request, acknowledgment and delivery. |
| Mechanical downtime | Heater and general faults grouped too broadly; repeat defects not visible | Tag failure mode/component; weekly Pareto; MTBF and MTTR by component. |
| Quality delay | First-off or alignment failures; delamination risk; glue/brown-sheet issues | Record defect, point of detection, disposition, affected length and parameter state. |

## 4.2 Critical bottleneck conclusion

The immediate bottleneck is the operating system around continuous flow, not a single proven machine-speed limit. The direct rewind study demonstrates a cycle faster than the RST10 target, while elapsed run records remain much slower. The gap is therefore dominated by waiting, change activity, restart delay, variation and downtime. Speed trials should occur only after these losses are measured and the quality window is protected.

## 4.3 Safety and quality constraints

Do not bypass doors, light curtains, dancer-bar pins, guarding, pinch-point controls, two-person metal-core lifting, crane rules or LOTO to gain cycle time.

Foot-pedal or controls changes require a documented risk assessment, validated stop behavior, updated electrical/control documentation and formal approval.

Any increased line or rewind speed requires a controlled trial that checks alignment, delamination, cut length, roll tightness, edges, belt contamination and stopping distance.

The proposed 2 min 30 sec restart expectation applies only to the repeat outfeed exchange where material remains available and the approved standard work permits parallel operation. It is not a blanket requirement for full material changeovers.

# 5 Desired state

## 5.1 Future operating condition

CAP2 runs to an approved product-specific standard. The next job and its consumables are confirmed before the current job ends. During normal rewind exchange, one operator owns safe unload, one owns core setup and restart, and the floating operator completes wrap, posting and replenishment without delaying the next cycle. Every stop is coded at the point of occurrence, and the crew uses an hourly board with a defined reaction when output falls behind.

## 5.2 KPI targets and definitions

| KPI | Definition | Initial state | Day 60 target | Day 90 control |
| --- | --- | --- | --- | --- |
| Good rolls/hour by product family | Accepted rolls / productive elapsed hours for the same approved SKU family | RST10 case study 6.06; other families to establish | RST10 pilot at least 8.0; approved targets for priority families | Each family meets its own released target for 5 comparable shifts. |
| RST10 pilot cycle | Elapsed production minutes / good RST10 rolls | 9.90 min | At most 7.5 min | Mean at most 7.5; 90th percentile at most 9.0 for RST10 only. |
| Repeat outfeed exchange | Cut complete to next winding motion; excludes full material change | To verify | At most 2:30 median | At most 2:30 median and 3:00 90th percentile. |
| Controllable downtime rate | Controllable stop min / scheduled production h | Establish Weeks 1-2 | 30% below baseline | 50% below baseline. |
| Material-feed loss | Minutes per material-feed event | 24.9 min average | At most 15 min average | At most 10 min average. |
| Material readiness | Jobs with full two-job kit / jobs due within horizon | Establish | At least 95% | At least 98%. |
| First-pass yield | Good without rework / total produced | Not supplied | Establish and no decline | At least 98% or approved product baseline, whichever is stricter. |
| Scrap rate | Scrap quantity / total material input for same SKU | Establish Weeks 1-2 | 20% below baseline | 30% below baseline with no hidden rework. |
| Downtime-code completeness | Stops over 1 min with valid reason and comment / all stops over 1 min | Not verified | At least 95% | At least 98%. |
| Layered audit score | Compliant checks / applicable checks | Not established | At least 85% | At least 90%. |

## 5.3 Product-specific target method

For each SKU, use the verified run-rate calculator as the starting standard, then validate it against at least 30 good cycles across at least three crews or operating conditions. The released target must specify setup time, constant-run time, repeat roll exchange, planned allowances and good-yield assumption.

| Product condition | Evidence-based initial planning value | Recommended launch target |
| --- | --- | --- |
| RST10 15 ft | Direct study 5.62 min; recorded 9.90 min; existing standard 7.5 min | 7.5 min/good roll; 8/hour; 80 per 10 productive hours. |
| Studied 25 ft condition | Direct study 12.56 min across only 2 cycles | Provisional 13.5 min/good roll; about 4.4/hour; 44 per 10 productive hours, pending 30-cycle study. |
| Other 15, 25, 50 or 54 ft families | Calculator values vary substantially by construction and setup | Release a target card by SKU family; never copy the RST10 target without validation. |

# 6 Improvement workstreams

## 6.1 Workstream A Baseline and daily management

| Action | Owner | Timing | Measure of completion |
| --- | --- | --- | --- |
| Create one shift log with scheduled minutes, planned stops, unplanned stops, good rolls, scrap, SKU and crew | Process Engineer | Days 1-3 | One reconciled record per shift; total time equals scheduled time. |
| Lock downtime taxonomy and event trigger of more than 1 minute | Operations and Engineering | Week 1 | Definitions posted; operators trained; duplicate codes removed. |
| Install hourly plan-versus-actual board by active SKU | Supervisor | Week 1 | Hourly entries and recovery action documented. |
| Complete 10-shift baseline across day and night crews | Process Engineer | Weeks 1-2 | Baseline report by SKU and crew with confidence ranges. |
| Hold 10-minute daily loss review and weekly Pareto review | Operations Manager | Start Week 2 | Top three losses have active owners and due dates. |

## 6.2 Workstream B Rewind flow and standard work

| Action | Technical detail | Target |
| --- | --- | --- |
| Define ready condition | Correct core inspected; wrap at point of use; crane and straps parked; WIP skid available; panel operator in position. | 100% of observed cycles ready before cut. |
| Separate restart from wrap | Where SOP and risk assessment permit, start the next winding cycle before finishing wrap and transfer of the completed roll. | No belt waiting caused by post-cycle work. |
| Assign restart owner | East Group 2 remains at panel during exchange and executes reset/start after all clear confirmation. | Restart signal within 10 sec of safe all-clear. |
| Increase rewind speed | Establish current recipe speed by SKU; trial small approved increments while checking roll tightness, wrap quality, tracking, dancer stability, braking and operator control. | Fastest validated speed becomes recipe standard; rewind time reduced at least 15% without quality loss. |
| Foot-pedal controls study | Measure pedal command, drive response, tension buildup, dancer movement and belt start. Check intentional delays and interlocks. | Cause confirmed; approved correction or documented standard. |
| Speed up crane cycle | Measure empty and loaded travel, lift, lower, attach and detach elements. Confirm manufacturer limits, load rating, stopping distance and control condition before any adjustment. | Pre-crane plus drop-off time reduced 25% with no unsafe motion or load instability. |
| Design hook-bar lifting aid | Create a rated hook-bar or spreader concept that self-locates on the roll lifting bar, reduces strap handling and keeps hands outside pinch points. Complete engineering calculation, risk assessment, proof-load test, inspection standard and operator trial before use. | Attachment and detachment time reduced 30%; zero dropped-load, pinch or roll-damage events. |
| Run 30-cycle confirmation | Record each element and abnormality by product and crew. | Median repeat exchange at most 2:30. |

### 6.2.1 Point of use 5S for rewind

| Item | Required condition | Control |
| --- | --- | --- |
| Cores | Store the active core sizes within safe reach of the rewind station, outside crane, forklift, egress and guarding envelopes. | Min-max quantity; labelled locations; replenish before shift and at breaks. |
| Wrap and tape | Mount at the wrapping position with one backup roll available. | Daily visual check; no searching during a cycle. |
| Lifting bars hooks and straps | Dedicated shadow-board or rack at the crane home position. | Pre-use inspection status visible; damaged equipment quarantined. |
| Knives and hand tools | Approved tools in fixed, labelled locations. | End-of-shift count and replacement trigger. |
| Empty core and scrap route | Clearly marked removal path and containers that do not block work. | Empty before capacity creates a stop. |

## 6.3 Workstream C Material feeding and changeover SMED

| External before stop | Internal while stopped | External after restart |
| --- | --- | --- |
| Verify next work order and revision; stage correct roll, rods, stabilizers, cores and tools; inspect material; position crane; confirm forklift; pre-enter recipe where controls allow. | Cut and secure old material; remove depleted roll; install prepared roll; align, overlap or thread; verify layers and recipe; first-off confirmation. | Return empty cores and packaging; close posting; replenish next-job kit; restore 5S without stopping the line. |

Video or directly observe 10 changes of each high-loss type. Classify every element as external, internal, motion, waiting, adjustment or required safety work.

Convert at least 50% of current internal preparation to external preparation by Week 6.

Use a two-job readiness board with red/amber/green status for material, core, pallet, recipe, work instruction, crane and forklift.

Create separate changeover standards for GRP, NPF/FF/RST and adhesive/fibermesh because their current averages differ.

### 6.3.1 Setup time reduction plan

| Step | Action | Measure |
| --- | --- | --- |
| Observe | Time at least 10 setups for each major setup family and record operator motion, crane time, adjustment, waiting and verification. | Element-level baseline and setup Pareto. |
| Separate | Classify work as external, internal, required safety work, adjustment, motion or waiting. | At least 50% of preparation identified as external. |
| Convert | Stage rolls, cores, rods, tools, pallets, recipe and work instruction before shutdown. | All external items green on readiness board before current run ends. |
| Simplify | Use marked positions, preset settings, quick identification, fixed tool locations and first-off checklist. | Fewer adjustments and searches; first-off accepted. |
| Parallelize | Assign safe simultaneous tasks by operator while preserving two-person and crane requirements. | No operator conflict or waiting for an available person. |
| Verify | Repeat 10 setups after changes and compare median and 90th percentile. | 30% median setup-time reduction by Day 60; 40% by Day 90. |

## 6.4 Workstream D Reliability and controls

| Action | Purpose | KPI |
| --- | --- | --- |
| Break mechanical code into heater, sensor, drive, belt, slitter, rewinder, crane and other | Make repeat failures visible | At least 95% component-level coding. |
| Tag each defect at machine and link to corrective work order | Prevent temporary fixes from disappearing | 100% of repeat or more-than-15-min failures linked. |
| Create top-five bad actor plan from two-week baseline | Concentrate maintenance resources | Top-five minutes down 30% by Day 60. |
| Verify critical spares and response plan for heater, sensors and drives | Reduce mean time to repair | Critical-spares gaps closed by Week 6. |
| Trend pedal, dancer and belt signals in PLC where feasible | Diagnose hidden sequence delay | Timestamped cause-and-effect trace completed. |

## 6.5 Workstream E Quality at source

Add a first-off and restart check for layer presence, alignment, bonding/delamination, edge condition, length, roll tightness and visual defects.

Record the machine recipe and material lot for each quality stop. Separate hold, rework and scrap quantities.

Define stop-call-wait criteria so operators do not continue creating suspect material, but also do not wait unnecessarily for known acceptable conditions.

Audit brown-sheet condition and replacement frequency; quantify the time and defects associated with sheet changes before changing the interval.

## 6.6 Workstream F Scrap material flow and minor-stop elimination

| Problem | Immediate control | Permanent countermeasure | Target |
| --- | --- | --- | --- |
| Scrap at belt exit or rewind | Provide correctly sized bins and remove before full; assign owner each shift. | Measure scrap by SKU and reason; correct cut, tracking, bonding or handling causes at source. | Scrap rate down 20% by Day 60 and 30% by Day 90. |
| Material will not flow or track | Stop before damage; realign layers; verify tension, guides, dancer, pinch roller and recipe. | Centerline settings by SKU; marked guide positions; component inspection; escalation after second repeat. | Material-flow stops down 50% by Day 90. |
| Material fixing and splicing delays | Stage approved tape, tools and replacement material; use a defined repair limit. | Create standard repair/splice method and stop criteria; train all crews. | Routine fix completed to validated standard without repeat failure. |
| Small recurring interruptions | Record every micro-stop over 30 sec for a two-week focused study, even if no formal downtime is opened. | Daily top-three petty-issue kaizen: assign owner, cause, fix and verification date. | Top 10 micro-stops reduced 80% by Day 60. |
| Scrap or empty-core handling blocks work | Clear route and containers before run; call pickup at trigger level. | Visual min-max and scheduled milk-run for scrap, cores and supplies. | Zero production stops caused by full bins or missing removal. |

## 6.7 Workstream G Hourly targets and operator support system

The screen at CAP2 will show the approved hourly target for the active product, the actual count, the current gap and the support status. The target must come from the released product-family target card. RST10 or any other product target must not be applied to a different product.

| Screen element | Required information | Purpose |
| --- | --- | --- |
| Active product | Item, work order and approved target-card revision | Prevent the wrong target from being displayed. |
| Hourly target | Good units expected this hour for the active product | Give the crew a clear and achievable production expectation. |
| Actual output | Live good-unit count from posting, scanner, PLC or verified manual entry | Show progress without waiting until the end of shift. |
| Gap and pace | Actual minus target; green, amber or red condition | Show whether recovery or supervisor support is required. |
| Loss reason | Operator-selected or automatic reason linked to downtime | Separate operator-controlled losses from external support delays. |
| Support status | Request time, acknowledgement, responder and arrival status | Confirm that the request reached the correct support group. |

### 6.7.1 Supervisor escalation logic

| Condition | System response | Supervisor response |
| --- | --- | --- |
| Green | Actual meets the approved hourly target | Continue normal monitoring. |
| Amber | One hour below the agreed warning threshold or pace predicts a miss | Review the cause with the operator and arrange recovery support. |
| Red | Output falls below the approved escalation threshold, two consecutive hours miss target, or a critical support call remains unanswered | Notify the shift supervisor with product, target, actual, gap, loss reason and requested support. Supervisor attends the line and assigns corrective action. |
| Safety or quality stop | Operator activates the appropriate call immediately regardless of output | Respond immediately. Production resumes only after the required release. |

Threshold approval: Operations must set the exact green, amber and red percentages after the two-week baseline. The first proposal can use green at 100% or above, amber at 90% to 99%, and red below 90%, but the plant must validate this by product and shift before release.

### 6.7.2 Operator support buttons

| Button | Destination | Information sent | Response measure |
| --- | --- | --- | --- |
| Material needed | Material handler and shift supervisor | Product, required material, quantity and required-by time | Acknowledgement and delivery time. |
| Scrap-bin pickup | Material handling or waste collection | Bin location, material type and fullness status | Acknowledgement and empty-bin return time. |
| Maintenance | Maintenance and shift supervisor | Asset, symptom, running/stopped condition and urgency | Acknowledgement, arrival and restoration time. |
| Quality support | Quality and shift supervisor | Product, defect, quantity at risk and last known good unit | Acknowledgement, arrival and disposition time. |
| Core packaging or forklift | Assigned support team | Item needed, location and urgency | Acknowledgement and fulfillment time. |

Each request must remain visible until acknowledged and closed. The system records call time, acknowledgement, arrival, completion and lost production minutes. Daily review assigns the delay to the correct cause so operator performance excludes time lost while waiting for material, maintenance, quality, forklift service or scrap-bin removal.

# 7 90 day implementation roadmap

| Phase | Timing | Main activities | Exit deliverables |
| --- | --- | --- | --- |
| Contain and measure | Days 1-14 | Clean time model; 10-shift baseline; downtime taxonomy; hourly board; observe feeding and rewind; confirm safety boundaries. | Signed baseline; top-three Pareto; verified RST10 and 25 ft samples; data-quality gap list. |
| Design and pilot | Days 15-30 | Draft standard work; point-of-use staging; two-job readiness; SMED trials; configure hourly target screen, alerts and support buttons; first-off checklist. | Approved pilot method; operator feedback; risk assessment; screen and button acceptance test; 30-cycle rewind dataset. |
| Implement and stabilize | Days 31-60 | Train all crews; release product-family target cards; activate supervisor alerts and support-response tracking; maintenance bad-actor fixes; daily tier review. | RST10 pilot at 8/hour; other priority families measured against their own standards; controllable downtime down 30%; audit score at least 85%. |
| Control and transfer | Days 61-90 | Control charts; layered audits; refine standards; close actions; document lessons and ownership. | Five comparable shifts on target; downtime down 50%; audit at least 90%; control plan active. |

## 7.1 Detailed action register

| ID | Action | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| A1 | Reconcile 169.05 production h and 621.05 downtime h to calendar and shift records | Process Engineer | D5 | Open |
| A2 | Remove or quarantine impossible production records and document rules | Data owner | D7 | Open |
| A3 | Complete 10-shift stratified baseline | Process Engineer | D14 | Open |
| B1 | Measure 30 repeat rewind exchanges and create element chart | Process Engineer | D21 | Open |
| B2 | Risk assess panel/foot-pedal and parallel-work changes | EHS and Controls | D21 | Open |
| B3 | Trial panel-owner method with safe all-clear signal | Supervisor | D28 | Open |
| B4 | Run controlled rewind-speed trials by priority SKU and release validated recipe speeds | Process Engineer and Quality | D35 | Open |
| B5 | Measure crane cycle and validate safe speed optimization within manufacturer limits | Maintenance and EHS | D30 | Open |
| B6 | Design, calculate, risk assess and proof-test hook-bar lifting aid | Mechanical Engineering and EHS | D60 | Open |
| C1 | Observe 10 GRP and 10 NPF/FF/RST changes using SMED sheet | CI Lead | D21 | Open |
| C2 | Launch two-job material readiness board | Planner and Supervisor | D21 | Open |
| C3 | Mark crane home, roll staging and point-of-use consumables | Supervisor | D30 | Open |
| C4 | Move approved core inventory to point of use and install visual min-max locations | Supervisor and EHS | D21 | Open |
| D1 | Create component-level failure codes and bad-actor list | Maintenance | D14 | Open |
| D2 | Complete controls trace for pedal-dancer-belt sequence | Controls | D30 | Open |
| D3 | Close top-three repeat mechanical causes | Maintenance | D60 | Open |
| E1 | Release first-off and restart quality checklist | Quality | D21 | Open |
| E2 | Launch scrap-by-SKU and defect-reason tracking with daily review | Quality and Process Engineer | D14 | Open |
| E3 | Create SKU centerline settings for alignment tension guides and dancer operation | Process Engineer | D45 | Open |
| E4 | Complete two-week micro-stop study and close top 10 petty issues | Supervisor and Maintenance | D45 | Open |
| G1 | Approve product-specific hourly target cards and screen data source | Operations and Process Engineer | D21 | Open |
| G2 | Configure hourly target actual gap and green amber red display | Controls and IT | D30 | Open |
| G3 | Configure material scrap maintenance quality and logistics call buttons | Controls and IT | D30 | Open |
| G4 | Approve escalation thresholds recipients and support response times | Operations Manager | D30 | Open |
| G5 | Pilot the screen alerts and buttons on all crews and correct failure modes | Process Engineer and Supervisors | D45 | Open |
| F1 | Train and certify all crews to released standard work | Training owner | D45 | Open |
| F2 | Run Day 60 gate review and adjust targets | Operations Manager | D60 | Open |
| F3 | Complete Day 90 control handoff | Operations Manager | D90 | Open |

# 8 Standard work and SOP change package

## 8.1 Proposed role design during normal roll exchange

| Role | Before cut | During exchange | After safe restart |
| --- | --- | --- | --- |
| East Group 1 | Confirm crane, skid, core and unloading path ready | Release chucks and lead safe crane removal; confirm area clear | Transfer finished roll and verify quality. |
| East Group 2 | Stand at panel; confirm next core and wrap available | Support chuck/core as required; return to panel; reset/start after all-clear | Wrap and post prior roll while monitoring cycle needs. |
| West operator | Maintain alignment and anticipate material depletion | Continue infeed monitoring; assist only when required by approved procedure | Prepare next material and protect continuous feed. |

Approval condition: This role design is a proposed future-state concept. EHS, Operations and Engineering must reconcile it with every two-person lift, crane, access and line-of-sight requirement in Rev 12 before release.

## 8.2 Required SOP edits

Add definitions for normal repeat roll exchange, full material changeover, planned stop, unplanned stop, productive time and good roll.

Add the safe use and exact purpose of the foot pedal, including response expectation, required all-clear and prohibited use.

Assign the panel and restart role explicitly during each cycle and state the verbal or visual all-clear protocol.

Require immediate posting after each roll and downtime coding for every stop longer than one minute.

Add product-specific target cards and the hourly plan-versus-actual response process.

Add two-job material readiness and early supplies-button criteria with a named owner.

Clarify which wrap, transfer, core and staging steps may occur in parallel and which require all operators.

Add escalation triggers for repeated faults, material shortage, quality abnormality and inability to meet the standard cycle.

Update training records, revision history, risk assessment and visual aids after the pilot is approved.

# 9 Control plan

| Control | Frequency | Owner | Trigger | Reaction |
| --- | --- | --- | --- | --- |
| Hourly plan vs actual by SKU | Hourly | East Group 2 or designee | Two consecutive hours below 90% | Record reason; supervisor removes constraint; set recovery plan. |
| Target screen and supervisor alert | Continuous with hourly reset | Controls system and Shift Supervisor | Approved amber or red threshold reached | Display gap; alert supervisor; acknowledge cause and assign support. |
| Support-call response | Every operator request | Material Handling, Maintenance, Quality or Logistics | Button remains unacknowledged beyond approved response time | Escalate to shift supervisor; record waiting minutes against the responsible loss category. |
| Top loss review | Daily | Shift Supervisor | Any event over 15 min or repeat event | Contain; assign action; open WO for equipment issue. |
| Material readiness | Two jobs ahead | West operator and material handler | Any red item inside one-job horizon | Escalate immediately; resequence only with planning approval. |
| Micro-stop log | Every interruption over 30 sec during focused study; then top recurring issues | East Group 2 | Same issue repeats twice in shift | Contain, tag cause, assign owner and verify fix at next tier meeting. |
| Core and tool point-of-use audit | Start of shift | East Group 2 | Missing core, tool, wrap or lifting device | Replenish before production; correct min-max or ownership failure. |
| First-off quality | Startup, changeover, restart after abnormal stop | Quality-trained operator | Any specification miss | Stop, contain since last good check, correct and reapprove. |
| Standard-work audit | Twice per week per crew | Supervisor | Score below 85% or safety deviation | Coach immediately; stop unsafe work; retrain before independent operation. |
| KPI control chart | Weekly | Process Engineer | Point outside limit or 7-point trend | Investigate special cause; do not change standard without evidence. |
| SOP review | After pilot and quarterly | Engineering and EHS | Process or control change | Risk assess, approve, revise and retrain. |

## 9.1 Daily tier board

Safety: incidents, near misses, unsafe conditions and open corrective actions.

Quality: first-pass yield, scrap/rework, holds and top defect.

Delivery: good rolls versus target by SKU and missed-order risk.

Cost and loss: downtime minutes by top reason, material waste and overtime where applicable.

People: staffing, training status and support required.

Actions: one owner and due date for every red metric; verify closure effectiveness, not only completion.

# 10 Verification and benefit calculation

## 10.1 Trial design

| Trial | Minimum sample | Pass criteria |
| --- | --- | --- |
| Repeat rewind exchange | 30 cycles per main condition; at least 3 operators/crews | Median at most 2:30; 90th percentile at most 3:00; zero safety/quality failures. |
| RST10 pilot target | Five comparable 10-hour productive windows or equivalent accumulated time | At least 8.0 good rolls/hour and first-pass yield maintained for RST10 only. |
| 25 ft standard | At least 30 cycles across representative products | Stable mean and variation; target no faster than safe demonstrated performance with allowance. |
| Material-feed improvement | At least 20 events after change | Average at most 15 min Day 60 and 10 min Day 90; no increase in defects. |
| Mechanical corrective action | Four weeks after closure | No recurrence or at least 50% reduction in failure minutes for addressed mode. |

## 10.2 Capacity model

Use good-roll hours gained, not gross machine speed, to value the program. For a product family:

Good rolls gained per shift = productive hours x (future good rolls/hour - baseline good rolls/hour)

For the RST10 product case study, increasing from 6.06 to 8.00 good rolls/hour over 10 productive hours adds approximately 19.4 good rolls per shift, a 32% increase for that product. Benefits for other products must be calculated from their own verified baseline and target; the RST10 gain cannot be generalized to the full CAP2 product mix.

## 10.3 Financial model to complete

| Benefit | Calculation | Required input |
| --- | --- | --- |
| Contribution from extra output | Additional good rolls x contribution margin per roll | Verified sales constraint and margin by product. |
| Downtime recovery | Recovered hours x constrained-line value per hour | Validated bottleneck value; avoid double counting extra output. |
| Scrap reduction | Avoided scrap quantity x material and disposal cost | Baseline scrap by defect and SKU. |
| Labor or overtime avoidance | Avoided overtime hours x burdened rate | Actual staffing and overtime records. |
| Maintenance saving | Avoided failures x parts plus labor plus lost-capacity cost | Failure history and WO cost. |

# 11 Baseline collection forms

## 11.1 Shift production record

| Date shift crew | SKU WO | Scheduled min | Planned stop min | Unplanned stop min | Good | Scrap rework | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |

## 11.2 Cycle observation sheet

| Cycle | SKU length | Setup | Rewind | Wrap | Pre crane | Drop off | Restart buffer | Total | Abnormality |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## 11.3 Downtime event record

| Start | End | Minutes | Category | Component | Reason facts | Containment | Owner WO |
| --- | --- | --- | --- | --- | --- | --- | --- |

# 12 Governance and decision rights

| Role | Accountability |
| --- | --- |
| Operations Manager | Sponsor; approve targets, staffing and gate releases; remove cross-functional barriers. |
| Process Engineer | Own baseline, studies, target cards, trials, analytics and control transfer. |
| Shift Supervisors | Own hourly execution, coaching, loss response and action escalation. |
| Operators | Follow standard work, stop for abnormalities, code losses accurately and contribute trial feedback. |
| Maintenance and Controls | Diagnose failures, validate control changes, execute corrective work and preserve safeguards. |
| Quality | Approve checks, disposition rules, trial quality results and first-pass-yield definition. |
| EHS | Approve risk assessments and changes affecting access, lifting, crane work, controls or guarding. |
| Planning and Material Handling | Maintain two-job readiness and respond to supply signals. |

# 13 Final recommendation

Launch the plan with a two-week measurement and containment sprint, then release only those method changes that pass safety, quality and repeatability gates. Use RST10 only as the first product-specific pilot because its supplied history supports comparison; do not use its 80-roll target as the CAP2 machine target. Build separate standards for every priority product family. The most valuable early work is to stabilize material feeding, major roll changes, material readiness, restart discipline and the pedal-dancer-belt sequence. Once the line is stable, product-specific speed optimization can safely capture the remaining capacity.

## Source notes

Internal sources reviewed: Time study CAP 2 Rewind; CAP2 Run rates spreadsheet PDF; CAP 2 Project Plan; CAP 2 Plan; Pliteq 084-SOP-001 CAP2 Rev 12. Calculations in this report are derived from the supplied values. Event-Pareto totals reflect the extractable coded-event sample and are intentionally kept separate from the YTD downtime summary.